## Sheet1
Blackboard Group No ?? Class XYY | Project kickoff |  |  |  |  | Version 1
SMART goals ==> | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
days
Each group member | Project Mgmt Activity | share with team |  |  | TO DO
Group Meeting Agenda ==> | create MS Team Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1 | Thrusday 1st december | TO DO | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. | 2 | Saturday Dec-3 | TO DO
[programmer 1] Hetav Action Items | Hetav will do the typing of Tokenizing part. | assigned at 2:19 pm EDT, Planned to submit on same day before 11:59 pm. Agreed to do so | 10 | Thrusday 1st december | DONE | Hetaav will do and Check Tokenizing part V1 again, submit it to the Team Lead (Harshil) with meaningful comments and constantly update his work status to the Team Lead | Hetav will submit his file to Professor for review on teams | 3 | Saturday Dec-3 | TO DO
[Team-Leader] Harshil Action Items | I will do the typing of fundamentals part, analyze other members' work, combine them and then submit it on BB | assigned at 2:19 pm EDT, Planned to submit on same day before 11:59 pm. Agreed to do so | 2 | Thrusday 1st december | DONE | I will do and Check fundamentals part V1 again with meaningful comments. I will also keep a track of all other members' work and combine it as well. | i will submit my file to Professor for review on teams | 2 | Saturday Dec-3 | TO DO
[programmer 3] Tapan Action Items | Aryan will do the typing of converting part. | assigned at 2:19 pm EDT, Planned to submit on same day before 11:59 pm. Agreed to do so | 4 | Thrusday 1st december | DONE | Aryan will do and Check Tokenizing part V1 again, submit it to the Team Lead (Harshil) with meaningful comments and constantly update his work status to the Team Lead | Aryan will submit his file to Professor for review on teams | 2 | Saturday Dec-3 | TO DO
[programmer 2] Aryan Action Items | Tapan will do the typing of Manipulating part. | assigned at 2:19 pm EDT, Planned to submit on same day before 11:59 pm. Agreed to do so | 3.5 | Thrusday 1st december | DONE | Tapan will do and Check Tokenizing part V1 again, submit it to the Team Lead (Harshil) with meaningful comments and constantly update his work status to the Team Lead | Tapan will submit his file to Professor for review on teams | 2 | Saturday Dec-3 | TO DO
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.